## Failed Tests
No. | Module | Test ID | Failed test | Priority | Severity | Issue group | Role | Steps to reproduce | Expected result | Actual result | Impact | Decision / note | Test doc | Evidence | Date found | Fix status | Assignee | Retest result | Comments
1 | Tutorial | TUT-08 | Artist edits an approved tutorial | P0 | High | Edit after approval skips review | Artist | 1. Artist creates a tutorial; admin approves it. 2. Artist opens Sunting, changes the title, saves. 3. Check the artist list and /resources/tutorials. | Item returns to 'Menunggu semakan' (or the change waits for admin approval). | Status stays 'Diluluskan' and the new title is public immediately. | An artist can change approved public content (title, description, URL) with no admin check. | Needs product decision (is re-approval required?). | docs/tests/tutorial/TUT-08-edit-approved-bypass.md | docs/tests/tutorial/evidence/tut-public-after-approve.png | 2026-09-25 | Open
2 | Perkongsian | SHR-09 | Galeri edits an approved perkongsian | P0 | High | Edit after approval skips review | Galeri | 1. Galeri creates a perkongsian; admin approves it. 2. Galeri edits the title and saves. 3. Check the dashboard and /resources/sharings. | Item returns to review, or the change waits for approval. | Stays 'Diluluskan'; new title 'QA Perkongsian Galeri 01 (Edit selepas lulus)' is public immediately. | Approved public content can be changed without admin review. | Needs product decision. Same root cause as TUT-08. | docs/tests/perkongsian/SHR-09-edit-approved-bypass.md |  | 2026-09-25 | Open
3 | Koleksi | KOL-10 | Artist / Galeri edits an approved karya | P0 | High | Edit after approval skips review | Artist, Galeri | 1. Artist (and Galeri) creates a karya; admin approves it. 2. Owner edits the title and saves. 3. Check the dashboard and /collection. | Item returns to review, or the change waits for approval. | Both stay 'Diluluskan' and the new title is public immediately. | Approved works can be changed without admin review. | Needs product decision. Same root cause as TUT-08. | docs/tests/koleksi/KOL-10-edit-approved-bypass.md | docs/tests/koleksi/evidence/kol-artis-edit.png | 2026-09-25 | Open
4 | Galeri | GAL-09 | Galeri owner edits an approved galeri | P0 | High | Edit after approval skips review | Galeri | 1. Galeri creates a galeri with a slideshow; admin approves it. 2. Owner opens Sunting, changes the title, saves. 3. Check the dashboard and the public galeri page. | Galeri returns to review, or the change waits for approval. | Stays 'Diluluskan'; the new title is public immediately (slug unchanged). | Approved public content can be changed without admin review. | Needs product decision. Same root cause as TUT-08. | docs/tests/galeri/GAL-09-edit-approved-bypass.md | docs/tests/galeri/evidence/gal-edit.png | 2026-09-25 | Open
5 | Art For Sale | AFS-10 | Artist edits an approved listing (title and price) | P0 | High | Edit after approval skips review | Artist | 1. Artist creates a listing at RM 1,500; admin approves it. 2. Artist edits the title and changes the price to 9999; saves. 3. Check the dashboard and /shop/art-for-sale. | Listing returns to review, or the change waits for approval. | Stays 'Diluluskan'; the new title and price RM 9,999 are public immediately. | An artist can change the price of an approved listing with no admin check; buyers see it at once. Highest business impact of this group. | Needs product decision. Same root cause as TUT-08. | docs/tests/art-for-sale/AFS-10-edit-approved-bypass.md | docs/tests/art-for-sale/evidence/afs-artist-edit.png | 2026-09-25 | Open
6 | Koleksi | KOL-09 | Admin changes Koleksi type on edit | P0 | High | Koleksi type not saved on edit | Admin | 1. Admin creates a work (Koleksi = Karya artis, default). 2. Sunting → set Koleksi to 'Koleksi Tetap Balai Seni Negara' → Simpan. 3. Reload; reopen Sunting; check the KOLEKSI TETAP counter and /resources/nag-collection. Repeat once. | Type changes; KOLEKSI TETAP counter goes 99→100; the work appears on /resources/nag-collection. | Toast says 'telah dikemas kini' but the type stays 'Karya artis' (counter stays 99, public page shows 0). Reproduced twice. Choosing Koleksi Tetap at creation works. | A work created in the wrong collection cannot be moved without deleting and recreating it. | Defect. | docs/tests/koleksi/KOL-09-edit-koleksi-type.md | docs/tests/koleksi/evidence/kol-koleksi-selected.png | 2026-09-25 | Open
7 | Pautan | PTN-05 | Invalid URLs accepted in the URL field | P0 | Medium | URL not validated | Admin | 1. Pautan → Tambah pautan; Nama 'QA Pautan Invalid', URL 'javascript:alert(1)'; Simpan. 2. Repeat with URL 'not a url with spaces'. 3. Open /links. | Rejected with a clear validation message (as the Berita link field does). | Both saved and published as https://javascript:alert(1) and https://not a url with spaces (broken links). Not executable because https:// is prepended. | A typo produces a broken public link; no validation on the form. Admin-only exposure. | Defect. | docs/tests/pautan/PTN-05-url-validation.md | docs/tests/pautan/evidence/ptn-js-public.png | 2026-09-25 | Open
8 | Portal Utama | PTU-08 | Banner button link not validated | P0 | Medium | URL not validated | Admin | 1. Portal Utama → Banner → Banner baharu; title BM required; Pautan butang 'javascript:alert(1)'; Simpan. 2. Open the homepage and wait for the slide; click the button. | Rejected with a validation message. | Saved without error. At display time the link becomes 'lert(1)' and the button goes to /lert(1) (404). Not executable. | Broken button on the live homepage banner; input never validated. | Defect. Same pattern as PTN-05. | docs/tests/portal-utama/PTU-08-banner-link-validation.md | docs/tests/portal-utama/evidence/ptu-banner-qa-slide.png | 2026-09-25 | Open
9 | Portal Utama | PTU-11 | Banner delete has no confirmation | P0 | Medium | Delete without confirmation | Admin | 1. Portal Utama → Banner tab. 2. Click Padam on a banner. | A confirmation dialog with Batal (as in every other module). | The banner is deleted on the first click; no dialog. | Accidental click can delete the live hero banner; cannot be undone. | Needs product decision; inconsistent with all other modules. | docs/tests/portal-utama/PTU-11-banner-delete.md | docs/tests/portal-utama/evidence/ptu-home-final.png | 2026-09-25 | Open

## Blocked Tests
No. | Module | Test ID | Test | Role | Why blocked | What is unverified | Test doc
1 | Art For Sale | AFS-08 | Hubungi Penjual contact form | Admin/anonymous | Valid submission asks the visitor to tick 'I'm not a robot' (reCAPTCHA v2). I did not bypass it. | Sending, the seller's Inbox and message text handling are unverified. A human can tick the box and the test can be finished. | docs/tests/art-for-sale/AFS-08-contact-seller.md
2 | Perkhidmatan | SVC-05 | Hubungi Pembekal contact form | Anonymous | Form opens with the same reCAPTCHA; not submitted. | Sending and the provider Inbox unverified. | docs/tests/perkhidmatan/SVC-05-contact-provider.md
3 | Cenderahati | MER-06 | Hubungi Penjual contact form | Anonymous | Form opens with the same reCAPTCHA; not submitted. | Sending and the seller Inbox unverified. | docs/tests/cenderahati/MER-06-contact-seller.md

## Summary
Issue group | Failed tests | Count | Highest severity | Suggested action
Edit after approval skips review | TUT-08, SHR-09, KOL-10, GAL-09, AFS-10 | 5 | High | Decide whether owners' edits to approved items need re-approval. If yes, send edited items back to "Menunggu semakan" (or hold the change). Likely one shared cause across modules; start with Art For Sale because the price is exposed.
Koleksi type not saved on edit | KOL-09 | 1 | High | Save the Koleksi type field on update (works on create).
URL not validated | PTN-05, PTU-08 | 2 | Medium | Add server-side URL validation like the Berita link field (require http/https; reject javascript: and spaces).
Delete without confirmation | PTU-11 | 1 | Medium | Add the same confirmation dialog used by other modules to banner delete.
Total failed tests |  | 9
Blocked tests (reCAPTCHA) | AFS-08, SVC-05, MER-06 | 3